## Sheet1
Implementation Planning Decision Log
Institution name:
Fields in the Decision Log are compiled and adapted from Foundational Sources (HealthMeasures.net, ISOQOL, PCORI, Biber et al) and other sources
as described in the Implementation Planning Guide for PROs, which is available at http://EASI-PRO.org in the “Resources” for Epic, Cerner, and OpenEMR.
All fields should be completed over the course of the planning project and may be completed in any order.
Implementation teams may modify the Decision Log as desired in order to fulfill the needs of the planning team.
Questions pertaining to the institution as a whole are placed at the end of this Decision Log.
An Implementation Plan Template is available at http://EASI-PRO.org that may be used to convert the information in this log to a readable and sharable plan.
Question | Sub-question | Response
Designate Project Team
Project-level roles: | Site leader and additional leaders
Technical personnel
Consulting and research assistance and other additional staff
Institution-level roles: | Persons to keep informed
Executive sponsor (e.g., VP) or equivalent
Implementation coordinator at the institution level, if existing
Institution-employed EHR IT person
Clinic-level roles: | Clinical champion
Operational leader/clinic manager or equivalent position
Process owner within the clinic (driving the PRO implementation at the clinic level [may be the clinical champion or operational leader])
Physicians and multi-disciplinary team who will use PROMIS in the clinic
Multi-disciplinary non-physician roles (not names) of persons who will interact with PROs in the clinic. I.e., APNs, PAs, Nurses, Social Workers, MAs.
Choose Pilot Clinic
PILOT CLINIC: | Please list the clinic you have chosen for your pilot:
Define Details of Target Population
What populations and patients are most suitable for collection and use of PRO data during the pilot implementation.
Which clinic will be the site of the pilot implementation? If a specific condition within a larger clinic will be the initial target, describe procedure or disease process.
What population of patients should complete the PRO(s) of interest.
Are there any special considerations for the population of interest? For example, if the population includes pediatric patients, at what ages will parents have proxy roles? Will parents need to approve submissions? Similarly, what about disabled patients or the cognitively impaired?
Exclusion criteria: Will any patients be excluded from the population of interest (e.g., patients flagged in Epic as requiring a translator, patients under 18 years old, etc.)
Describe who you would like to complete a specific assessment. Some example populations include:
* Patients with an appointment with a specific clinician or in a specific clinic
* Patients with a specific procedure code
* Patients with a specific diagnostic code
* Patients with a specific order (e.g., pre-hip replacement surgery order set)"
"Generate a description. Examples:
* All adult patients scheduled for an appointment with a medical oncologist in the Comprehensive Cancer Center. This includes new and established patients.
* All adult patients who have order placed for a total hip replacement, total knee replacement, revision hip surgery, or revision knee surgery."
Describe expected volume (in either numbers or more general terms)
Consider Purpose, Barriers, and Evaluation
May customize and mark n/a if appropriate.
PROs should be used when the goals of clinical care will be enhanced by collecting data directly from patients in a systematic and validated manner.
While clinicians can ask individuals patients about their individual outcomes, PROs offer the advantage of collecting and understanding how patients are doing relative to a large group of similar patients.
PROs generally do not replace clinical conversations, but they may enhance the clinical conversation and give clinicians information they would not otherwise be able to gather.
Please record the thoughts and views of clinical champion and other leaders with regard to the following questions:
Purpose | Describe the primary aims for use of PROs in this setting (e.g., diagnosis, screening, monitoring a symptom/outcome, to meet guidelines).
Purpose | What benefit(s) are anticipated from the use of PROs? What do the physicians and the interdisciplinary team expect to accomplish due to the introduction of PROs? In other words, what are the clinical goals of having direct-from-the-patient information available?
Purpose | How do clinicians anticipate that care will change (if at all) as a result of having access to patient-reported information?
Purpose | Are there any regulatory or external requirements that would be fulfilled by utilizing PROs? Note any deadlines.
Purpose | Will PROs also be used for research now or in the future?
Evaluation | What will you measure to demonstrate the impact of PROs?
Evaluation | Closely related to expected benefits, how will clinicians define “success” for this pilot? What factors are most important or least important to success?
Barriers | What barriers do clinicians foresee that may hamper the implementation of PROs in the clinic?
Barriers | Are there any processes currently used, sanctioned, or promoted by your institution that will potentially come into conflict with your planned use of PROMIS in the pilot clinic? If so, describe potential resolution.
Barriers | Have all providers in this clinic committed to implementing PROs? Do you have buy-in from the clinical team for implementation of PROs? If not, what are the implications of not having buy-in? Will PRO use be considered exploratory or optional?
Barriers | Are there any ethical or legal issues that should be considered?
Choose PROs
Select PRO measures that provide information that care providers and patients can use. Use encourages continued completion.
CHOOSE PRO(s) TO USE: Start by watching: https://youtu.be/Tq1BM7CeZTg
“The most critical thing for the pilot projects is to identify the relevant domains of self-reported health to assess in a given clinic.”
Read over these short documents:
Guides for measures to use in specific patient populations (e.g., OA/RA, COPD, Heart Failure, JIA) | http://www.healthmeasures.net/applications-of-healthmeasures/guidance/recommended-healthmeasures
http://www.healthmeasures.net/images/applications/What_you_need_to_know_before_requesting_PROs_in_your_EHR_Aug22_2017.pdf
http://www.healthmeasures.net/images/applications/Guide_to_Selection_of_a_HealthMeasures_06_09_16.pdf
· Consider measures available in your EHR | List depends on your installation. An example list is included in the Implementation Planning Guide.
· Consider patient | The health condition or disease of the population will inform the outcomes that need to be assessed. For example, physical functioning is critical for arthritis patients.
population | Global measures (e.g., physical health) are less informative for an individual patient than a narrower construct (e.g., fatigue)
LIST CHOSEN PILOT PRO(S): | Number 1
Number 2
Number 3
Number 4 (add lines if necessary)
Having chosen a measure or set of measures, familiarize yourself completely with the measure(s), reviewing a copy of the measure as it is to be displayed to a patient, and noting all questions and potential responses.
Workflow analysis/Finding time for PROs - & - PRO delivery and location
Workflow analysis - Finding time for PROs
Start by watching https://youtu.be/FKPG9zVLU64
“The most successful implementations find the little bits of unused time in the clinic workflow and put them to good use in completing PROs.” --N.Rothrock
Collecting PROs in clinical settings requires time from providers, staff, and patients: * Ordering assessment * Completing assessment * Following up on incomplete assessment * Reviewing and addressing results
Assemble a multi-disciplinary team to identify a strategy that minimizes disruptions.
Create time for a patient to complete an assessment prior to provider visit (e.g., schedule assessment appointment 20 minutes before visit).
Have a plan for patients who did not complete an assessment.
Clearly define roles (e.g., who checks that assessment was completed, who answers technical questions, who cleans and charges devices used for data collection).
Address any workflow issues after implementation.
Utilize existing wait time for patients to complete an assessment.
Reference: http://www.healthmeasures.net/applications-of-healthmeasures/guidance/for-integration-in-clinical-settings
PRO Delivery and Location
Decide where patients will be when they fill out PRO questionnaires and what staff will direct patients and set up machines if PROs are to be completed on site.
Examples: Patient completes assessment at home on a computer via mobile device. Patient completes an assessment in a specific clinic on a tablet? at a kiosk?” In an exam room?
Where do you expect the patient is physically located when completing a PRO Assessment?
Using your EHR's Patient Portal can aid in collecting information from patients. If measures will be sent via patient portal, what is the portal utilization rate? How can you increase the use of MyChart?
What is the workflow for patients who have not completed their PROs prior to a visit? What are moments of downtime or places in clinic workflow where patients might respond in the clinic to PRO questionnaires, assuming not all patients complete questionnaires at home? (Note that most institutions have found that patients do not always complete questionnaires at home.)
If patient is expected to complete the PRO on site, or has that option, who will set up the PRO for the patient and when will the patient be allowed time to complete the PRO questionnaire(s)? How will the person who will start the PRO for the patient know that s/he should take this action?
Consider clinicians and staff in the chosen clinic as well as the time structure and load within the clinic itself. Is at least a core group of physicians on board with investing the time and change in practice required for PROs?
Who will follow up on an incomplete assessment, when, and how, assuming followup will be done?
Ordering, triggers and assessment intervals
Start by watching https://youtu.be/QGiBt2d0Y40
Although it is possible to set up ad hoc ordering for PROs, for the pilot, we recommend deciding on triggers that will automatically generate a PRO request to the patient.
Number of assessments: Frequent assessments provide a more complete picture of a person’s health over time but can be burdensome to complete and review.
Measures may be completed at a healthcare visit or between clinic visits. Between visits allows more frequent assessment and less workflow disruption, but may not reflect how a person is doing on the day of a clinic visit and may require follow-up with people who are having problems or concerns.
Reference: http://www.healthmeasures.net/applications-of-healthmeasures/guidance/for-integration-in-clinical-settings
“Describe when PROs should be made available to respondents. What triggers a PRO assessment?” Examples: Always prior to a specific type of appointment? OR On a fixed schedule (e.g., 2 weeks, 1 month, 3 months after intervention)? OR In conjunction with a specific procedure or diagnosis? If so, list ICD or CPT codes that should trigger administration. OR Using a combination of triggers, for example: Before the first appointment, then at 3, 6, and 12 months thereafter. “Explain timing for administration including: all points in a series if administered as a series, how many days in advance of a time point the questionnaire should be sent, how long the questionnaire should be available for a patient to answer, whether you want a lockout period when no questionnaires should be sent, and whether you would like reminder emails sent."
Should trigger apply to all new patients (in which case, define “new”) or to all patients, both established and new?
Will patient demographics affect PRO ordering? For example, must patient be a certain age or a certain gender?
"If you want reminder emails, please also include the timing you would like for the reminder emails. Write reminder messages out in full.”
“What triggers the schedule to start (e.g., date of surgery, date of discharge from hospital)?" Is there any event that changes the schedule?
What is the “availability window” around each assessment? For example: Assessment available 7 days before and 2 days after a specific type of appointment.
Will patients have the ability to completely opt out of receiving PROs? If so, who will collect opt-out requests and how will that information be transmitted/ implemented in the system?
Handling results
Consider how clinicians will be notified about the existence of PRO data and how PRO data will be acted upon.
“PRO scores are available in the EHR after a patient completes an assessment. Sometimes, there may be an interest in pushing a notification about a specific score to a provider. For example, this is sometimes seen with scores indicating severe depressive symptomatology.”
Here is one example for illustration: “Scores above 80 on measure Z indicate severe depressive symptoms. The social work team within our clinic should be notified of the score indicating severe depressive symptoms. The social work team has a protocol in place for addressing patients’ depressive symptoms.”
This is another area where your local EHR team can share what options are available within your organization.
EHR Display: | How will PRO data be displayed in the EHR?
Do providers want to review scores outside of clinical visits?
Who else needs to review the score (e.g., regulatory or population health teams), and will it be accessible for reporting?
Will other teams know that a recent score is available and the PRO measure does not need to be asked again?
Notification Thresholds: | Are notifications about receipt of ALL PRO scores required? In other words, do you want to send both regular alerts and special alerts, or only special alerts? · If clinicians should be alerted about all PRO scores, what notification should be sent? To whom? Generate a detailed description and include notification text for each notification to be sent. · Do you want to use Inbasket messages for notifications about ALL scores?
Should scores above or below a certain threshold be treated differently or generate special alerts? In other words, is there a specific score or score threshold for a measure that should generate a notification to a clinician, providing a message letting him or her know that a PRO result is available? · List the values that you would like to flag as outside of normal limits for each of your PRO measures. · If ALL PROs will not generate Inbasket messages, list the threshhold trigger values for Inbasket messages.
Actions to be taken: | Are there scores that should trigger particular actions on the part of clinicians or others?
What action should be taken in cases in which such scores are received?
Technical and financial preparation
It will be necessary to team up with technical personnel to ensure that implementations are technologically sound.
Particularly, sites that plan to provide tablets for patients to use in order to answer questionnaires in the clinic or waiting room will need to ensure that tablets are set up and function properly over time.
Technical implementation | Do you have resources or funding to finance implementation or will your institution finance the technical work required to accomplish technical implementation of electronic PROs?
Who will perform necessary in-clinic technical tasks for smooth implementation, such as creating an implementation checklist for clinics, ordering tablets on time, and ensuring a smooth physical rollout? (See Part IV, Section 3.)
Who will liaise with the technical team to convey information and configure the clinic (and new clinics as they come online over time)?
If tablets will be available in the clinic for filling out PROs, how will the tablet devices be chosen, configured, and paid for? By whom and on what schedule? Who will configure tablets or kiosks and support them when problems arise? Who will create an asset management model with an established product life cycle for tablets and create a “gold image” for the tablet, perhaps with the use of a Mobile Device Manager? How will tablets be stored, cleaned, and charged?
Who will set up IT trouble ticket support system? How will trouble tickets be submitted and resolved?
Who will provide go-live support for any connectivity issues? Who will be on hand during go-live to answer PRO questions and offer other technical support?
Training | How will users be trained and engaged?
Who will create training materials?
Who will perform training?
Who will be trained (e.g., MAs, nurses, physicians, social workers)?
Ongoing support | Who will support the application on an ongoing basis, both technically and administratively?
Timing of the implementation
Questions relating to timing: | When will the pilot implementation roll out at your institution?
What are dates for ordering necessary equipment?
How long will the implementation be considered a “pilot” implementation?
Are there current plans to begin another pilot or a more general rollout, assuming general success of the pilot implementation? When and on what schedule, if known?
Evaluation planning- sociotechnical, metrics, patient feedback
Evaluation can take the form of qualitative evaluation and/or examination of metrics.
Qualitative sociotechnical evaluation can provide deep information about the psychosocial surround of the implementation. A good socio-technical fit is critical to long-term project success. Qualitative analysis can help answer the question of whether and how the clinic, clinicians, and patients are benefitting from PROs.
Questions relating to qualitative socio-technical evaluation | How will the pilot implementation be evaluated (i.e., what evaluation tool will be used to evaluate the overall success of the implementation)?
Metrics (usage statistics) key project information to help understand how much is being done and how numerically successful the implementation is.
Questions relating to metrics and analytics | List the usage outcome measures/metrics to be used in evaluation.
Getting the data: Who is tasked with pulling, assembling and formatting usage metrics and from what resource on what timeframe?
Using the data: Who will examine the metrics, on what schedule, and how will such metrics be used?
At times, institutions wish to solicit feedback from patients or provide patients with information about how PROs are being used and their benefits. This section is optional. Note that institutions who wish to interact with patients may need to obtain IRB approval.
Questions relating to patient feedback | If you plan to solicit patient feedback OR provide information to patients in connection with this pilot project, describe your patient feedback strategy (noting any plans to incorporate patient feedback into PRO design).
Institutional Support and Governance
NOTE: If you do not know the answer to the following questions or if the answers depend on the outcome of this pilot, it’s not necessary to answer at this moment, but these institutional issues should be borne in mind.
Questions relating to institutional support | Who are key stakeholders at the institutional level for this project?
Are leaders at the highest levels aware of this pilot project?
Does the PROMIS pilot initiative have institutional support? Is the institution pressing for implementation of PROs, or is this a demonstration project designed to understand the value of PROs and consider their future use?
What are the top priorities of key stakeholders at the institutional level in regard to collection of PROs within the pilot clinic or within the institution on a larger scale?9 In other words, why does the institution want to implement PROMIS (assuming it does). What benefit(s) are anticipated from the use of PROs? Describe the primary aims for the institution’s use of direct-from-the-patient information (e.g., diagnosis, screening, monitoring a symptom/outcome to meet guidelines).
Closely related, how do senior leaders define “success” for this pilot? What is most important or least important to success? Do you feel clinicians and administrators are aligned in how they think about success for PRO implementation? What are the main areas of synergy? Where do you anticipate a divergence of opinion?
What barriers do senior leaders foresee that might hamper the implementation of PROs at the institution?
Are there any processes currently used, sanctioned, or promoted by your institution that will potentially come into conflict with your planned use of PROMIS in the pilot clinic? If so, have you held appropriate conversations to ensure that the institution is behind this pilot project and to resolve any conflicts?9
Are there any regulatory or external requirements that would be fulfilled by utilizing PROs?
Will PROs also be used for research now or in the future?
Are there any ethical or legal issues that should be considered?
How will you manage conflicts that may arise between team members or within the organization? (Relates to organizational culture.)
Question for future consideration: For this pilot, we will create a pilot project protocol which will serve as the project charter. Future projects, however, may benefit from written parameters. Who will create future project charters and on what schedule?
Will you designate an implementation coordinator at the institution level (This person receives new requests for PROs in clinics and helps determine eligibility. This position may not be currently in existence.)
Although one or two PRO measures used in a single clinic probably won’t require a lot of governance, growth should be expected over time. As such, it is appropriate to consider up front how PROs will be governed, both at the institutional level and at the clinic level.
Questions relating to governance and oversight | Is there an oversight body related to EHR-embedded PROs within your organization?4
Are there guidelines or limits related to EHR-embedded PROs that must be followed?
Looking ahead, will your institution have a “core” measure or set of measures to be used in every clinical setting? Or will each setting choose the measures most relevant to itself?
Will the institution establish a frequency for core measures, and will that mesh with clinical PRO schedules?
Will patients be expected to fill out measures from different clinics simultaneously?
Will you create an executive steering committee or other governing body, if one does not now exist? Who will lead and who will serve on the executive steering committee or other governing body?
How will you manage conflicts that may arise between team members or within the organization? This question relates to organizational culture.
Question for future consideration: For this pilot, we will create an implementation plan that will serve as the project charter. Who will create future implementation plans and on what schedule?